**Tidsplan for Moderniserings Projekterne (the Modernization Projects)**

* TSS HCV Ørstedværket:
	+ start Civil Work Nov 2020 (including HV cable trenches)
	+ start installation electrical equipment April 2021
	+ Hand-Over: Dec 2021
* TSS Roskilde
	+ start Civil Work Nov 2020 (including 1st HV cable trenches)
	+ start installation electrical equipment April 2021
	+ Partial Hand-Over: Dec 2021
	+ Dec 2021: preparation 2nd HV trench
	+ Final Hand-Over: August 2022
* TSS Marslev
	+ start Civil Work July 2021 (including 1st HV cable trenches)
	+ start installation electrical equipment Dec 2021
	+ Partial Hand-Over: August 2022
	+ August 2022: preparation 2nd HV trench
	+ Final Hand-Over: April 2023
* TSS Fredericia
	+ start Civil Work Jan 2022 (including 1st HV cable trenches)
	+ start installation electrical equipment June 2022
	+ Partial Hand-Over: Feb 2023
	+ Feb 2023: preparation 2nd HV trench
	+ Final Hand-Over: October 2023
* TSS Slagelse
	+ start Civil Work April 2022 (including HV cable trenches)
	+ start installation electrical equipment Sept 2022
	+ Partial Hand-Over: May 2023
	+ May 2023: preparation 2nd HV trench
	+ Final Hand-Over: January 2024

#