**Tidsplan for Moderniserings Projekterne (the Modernization Projects)**

* TSS HCV Ørstedværket:
  + start Civil Work Nov 2020 (including HV cable trenches)
  + start installation electrical equipment April 2021
  + Hand-Over: Dec 2021
* TSS Roskilde
  + start Civil Work Nov 2020 (including 1st HV cable trenches)
  + start installation electrical equipment April 2021
  + Partial Hand-Over: Dec 2021
  + Dec 2021: preparation 2nd HV trench
  + Final Hand-Over: August 2022
* TSS Marslev
  + start Civil Work July 2021 (including 1st HV cable trenches)
  + start installation electrical equipment Dec 2021
  + Partial Hand-Over: August 2022
  + August 2022: preparation 2nd HV trench
  + Final Hand-Over: April 2023
* TSS Fredericia
  + start Civil Work Jan 2022 (including 1st HV cable trenches)
  + start installation electrical equipment June 2022
  + Partial Hand-Over: Feb 2023
  + Feb 2023: preparation 2nd HV trench
  + Final Hand-Over: October 2023
* TSS Slagelse
  + start Civil Work April 2022 (including HV cable trenches)
  + start installation electrical equipment Sept 2022
  + Partial Hand-Over: May 2023
  + May 2023: preparation 2nd HV trench
  + Final Hand-Over: January 2024

# 